## Backlog
Item | Priority | Work | Description
World/Map | 1 | 40 |  | Sprintin pituus 2 vko
Creatures | 2 | 40 | Player, monsters | Yhteydenpito e-posti (väh. 1 / viikko) ja miiting (1 / 2viikkoa)
Movement | 3 | 25 | How player and monsters move
AI | 4 | 20 | How monsters react to player's actions | 5 ekaa tärkeimpinä
Fight | 5 | 10 | Engine for fighting
GUI | 6 | 15 | Additional views (Fightlog, Inventory etc.)
Inventory | 7 | 5 | Inventory for player's equipment
Graphics | 8 | 5 | Will be created and added when needed
Controls | 9 | 4 | Additional controls (pause, quit, save, etc.)
Equipment | 10 | 10
Saving | 11 | 5
Menu | 12 | 5 | Main menu
Options | 13 | 3 | Options menu
Manual | 14 | 1
Story | 15 | 2
Vehicles | 16 | 5
GameModes | 17 | 4 | Additional games modes (survival, etc.)
Sounds | 18 | 5
Editor | 10 | 20 | Editor for making the map and villain files
224

## Task-list
Completed-tasks
World/Map | Creatures | Movement | AI | fight | GUI | Graphics | Controls | Other | Editor
Playarea for the game | Design | Moving the Hero | Design | fight action for Hero | Design | Design | Design | Meetings | Design
Different terrains for the map | integration | Moving villains | Integration | fight action for villain | Integration | Integration | Integration | Studying | Integration
Read map from a file | Testing | Checking for obstacles | Testing | design | Testing | Testing | Testing | Presenting | Testing
Borders for the map | Stats/Skills | cannot move through obstacles | reafactoring | integration | Fight log | creature icons | Controls for moving the hero | documentation | Documentation
Testing | Experience/Level up | Buffer for moving the map | Alignments for villains | testing | Writing to the fightlog | Terrain icons |  | commenting | converting drawn map to map file
Design | Terminating creatures |  | Actions for different alignments | stat-relation | Stat log |  |  | additional design | converting added villains to villain file
Integration | Reading villains from a file |  | Randomizing movement | critical hits | Updating stat log |  |  | additional refactoring | villain database
Move the map while player moves | Refactoring |  | Prevention for getting stuck | alignment relation | Functions for manipulating the logs |  |  | Code cleanup | adding villains
Painting the map | Integrating hero fight |  | chasing target | target relation | Spaces for logs |  |  | Additional testing | drawing map
Assigning creatures to spaces | Integrating villain fight |  | Choosing target | strike |  |  |  |  | User Interface
updating the map | Table for villains |  | changing alignment if attacked | check for target death |  |  |  |  | controls
| Creature graphics handling |  |  | check for own death |  |  |  |  | random generators
| Creature collision |  |  | Experience gain |  |  |  |  | editor for creatures
| sightRadius for villains |  |  | Health loss
Targeting for villains
skill-stat relation
Functions for skill/stat manipulation
painting the creatures
updating creature graphics

## Estimates-Done
Sprint | Estimate | Done | Remaining | Ideal
1 | 15 | 5 | 219 | 211.5556
2 | 10 | 5 | 214 | 199.1111
3 | 20 | 7 | 207 | 186.6667
4 | 12 | 15 | 192 | 174.2222
5 | 10 | 0 | 192 | 161.7778
6 | 10 | 15 | 177 | 149.3333
7 | 25 | 12 | 165 | 136.8889
8 | 20 | 5 | 160 | 124.4444
9 | 10 | 5 | 155 | 112
10 | 5 | 7 | 148 | 99.5556
11 | 10 | 10 | 138 | 87.1111
12 | 10 | 15 | 123 | 74.6667
13 | 10 | 20 | 103 | 62.2222
14 | 25 | 20 | 83 | 49.7778
15 | 25 | 5 | 78 | 37.3333
16 | 5 | 5 | 73 | 24.8889
17 | 5 | 3 | 70 | 12.4444
18 | 3 | 1 | 69 | 0